## Community Matrix
Goal | Policy | ID | Strategy | PPP | Detail | Timeline |  |  |  | Funding Source | Implementors
[6 empty] | 0-2 | 3-5 | 6-10 | Ongoing
Community Programs and Livability
C1. Ensure Hill District residents can have all their basic needs met within a 20-minute walk or roll of their home. | Promote accessibility. New development in the Hill District should incorporate diverse uses and prioritize universal accessibility. | C1.1 | Accessible community shared spaces | Project | Identify inclusive areas within the Hill District that offer access to all residents despite ability and increase the ability of residents and visitors to enjoy those spaces. |  | X |  |  | Pittsburgh Regional Transit | The Hill Registered Community Organizations, Pittsburgh Regional Transit
C1. Ensure Hill District residents can have all their basic needs met within a 20-minute walk or roll of their home. | Promote accessibility. New development in the Hill District should incorporate diverse uses and prioritize universal accessibility. | C1.2 | ADA accessible community facilities | Project | Evaluate community facilities based on ADA accessibility and develop a list for retrofitting priorities. |  | X |  |  | None needed | Department of Mobility and Infrastructure
C1. Ensure Hill District residents can have all their basic needs met within a 20-minute walk or roll of their home. | Support community activities on public streets. Hill District public streets should be designed to accommodate both temporary and permanent functions that support various community activities. | C1.3 | Shared streets | Project | Designate shared streets where pedestrians, cyclists, and vehicles can coexist in addition to being adaptable for community events and activities. |  | X |  |  | None needed | Pittsburgh Regional Transit; Department of Mobility and Infrastructure
C1. Ensure Hill District residents can have all their basic needs met within a 20-minute walk or roll of their home. | Create age-friendly buildings. Future building designs should be friendly to all ages and supports a universally designed, age-in-place neighborhood. | C1.4 | Universal design principles | Project | Adopt universal design principles for new development in the Hill Distrist that promote flexible spaces that accommodate a range of preferences and abilities, minimize hazards, and are communicated effectively to individual users. Potential components could include open floor plans, no-step entries, clear signage, wider sidewalks, and shaded paths. This should build off the existing URA design guidelines. |  |  | X |  | None needed | Department of City Planning
C2. The Hill District will focus on long-term community resilience, with self-sufficiency, equity, representative leadership and governance, and improved health outcomes as guiding principles. | Improve health outcomes for Hill District residents. Health outcomes in the Hill District should be improved through a blend of community-based interventions and strategic long-term planning. | C2.1 | Communal initiatives and partnerships | Partnership | Address health disparities and racial bias through individual, and communal initiatives and intentional partnerships with government agencies, health institutions, and community organizations that offer awareness and solutions to the pressing health issues in the Hill District. This could include health fairs, mobile health clinics, community clean-ups, etc. |  |  |  | X | Allegheny County Health Department | Allegheny County Health Department
C2. The Hill District will focus on long-term community resilience, with self-sufficiency, equity, representative leadership and governance, and improved health outcomes as guiding principles. | Improve health outcomes for Hill District residents. Health outcomes in the Hill District should be improved through a blend of community-based interventions and strategic long-term planning. | C2.2 | Hill District Health Action Plan | Partnership | Partner with the Allegheny County Health Department to develop the Hill District Health Action Plan to increase awareness around chronic health issues and address pressing health concerns in the Hill District. |  |  | X |  | Allegheny County Health Department; State and Federal Grants | The Hill Registered Community Organizations, Allegheny County Health Department
C2. The Hill District will focus on long-term community resilience, with self-sufficiency, equity, representative leadership and governance, and improved health outcomes as guiding principles. | Promote economic stability. Economic stability in the Hill District should be promoted through investments in financial education, capacity-building, sustainable employment, and community ownership. | C2.3 | Entreprenurial resources | Partnership | Create, expand and collaborate with institutions and organizations to provide resources, mentorship and capacity for entrepreneurs, small businesses, and residents seeking self-employment. |  |  |  | X | State and Federal Grants; Office of Management and Budget, Urban Redevelopment Authority | The Hill Registered Community Organizations, Community Based Organizations
C2. The Hill District will focus on long-term community resilience, with self-sufficiency, equity, representative leadership and governance, and improved health outcomes as guiding principles. | Promote economic stability. Economic stability in the Hill District should be promoted through investments in financial education, capacity-building, sustainable employment, and community ownership. | C2.4 | Community ownership | Program | Enable the community to capitalize on the opportunity and potential in abandoned and vacant properties by expanding upon the Vacant Property Recovery Program. |  |  | X |  | Urban Redevelopment Authority, State and Federal Grants | Urban Redevelopment Authority, The Registered Community Organizations, Community Land Trusts, Pittsburgh Land Bank
C3. A mix of new and rehabilitated housing will serve multiple generations of Hill residents without displacement of existing residents and reduce barriers to housing development and preservation of historic black spaces. | Improve housing standards. Safe, healthy living conditions should be promoted for residents in addition to access to resources to help determine the livability of a space prior to signing a lease. | C3.1 | Landlord and tenant engagement | Program | Inform and educate landlords, tenants, and the community regarding rights and responsibilities of property managers and renters. |  |  |  | X | None needed | Pittsburgh Housing Authority
C3. A mix of new and rehabilitated housing will serve multiple generations of Hill residents without displacement of existing residents and reduce barriers to housing development and preservation of historic black spaces. | Improve housing standards. Safe, healthy living conditions should be promoted for residents in addition to access to resources to help determine the livability of a space prior to signing a lease. | C3.2 | Home maintenance assistance programs | Program | Secure additional funding and partner with local organizations to increase the ability for landlords and homeowners to maintain safe and healthy living conditions. |  |  | X |  | State and Federal Grants, Philanthropy | Urban Redevelopment Authority, Housing Authority
C3. A mix of new and rehabilitated housing will serve multiple generations of Hill residents without displacement of existing residents and reduce barriers to housing development and preservation of historic black spaces. | Improve housing standards. Safe, healthy living conditions should be promoted for residents in addition to access to resources to help determine the livability of a space prior to signing a lease. | C3.3 | Estate planning services | Program | Connect residents with legal aid organizations that offer affordable estate planning advice and assistance. |  |  |  | X | None needed | Legal Assistance Providers, The Hill Registered Community Organizations, Community Based Organizations
C3. A mix of new and rehabilitated housing will serve multiple generations of Hill residents without displacement of existing residents and reduce barriers to housing development and preservation of historic black spaces. | Improve housing standards. Safe, healthy living conditions should be promoted for residents in addition to access to resources to help determine the livability of a space prior to signing a lease. | C3.4 | Hill District Cooperative Housing & Development Guidebook | Project | The guidebook should serve as a resource for individuals and groups interested in establishing and managing cooperative housing, providing guidance on cooperative housing models, planning and development, legal and regulatory considerations, and financial management. |  | X |  |  | State and Federal Grants, Department of City Planning, Urban Redevelopment Authority | Department of City Planning, Urban Redevelopment Authority
Cultural Heritage and Preservation
C4. The future of the Hill District will build upon and further emphasize the neighborhood’s African American cultural legacy and preservation. | Cultivate a community responsive to changing needs. The Hill District should be a resilient community that can adapt to various economic challenges while preserving its historic and cultural assets. | C4.1 | Capacity building | Partnership | Increase capacity at community organizations, i.e. non-profits and institutions assisting residents access resources through technical assistance in accessing federal and state funds. |  |  |  | X | Urban Redevelopment Authority | Nonprofit organizations, Urban Redevelopment Authority
C4. The future of the Hill District will build upon and further emphasize the neighborhood’s African American cultural legacy and preservation. | Cultivate a community responsive to changing needs. The Hill District should be a resilient community that can adapt to various economic challenges while preserving its historic and cultural assets. | C4.2 | Public realm improvements | Project | Establish public realm experiences that express the character and history of the Hill District community, including the Heritage Walk, Cultural Legacy Loop, Crossroads Public Realm Improvements, Kirkpatrick Crossroads pilot, and other such efforts. |  | X |  |  | State and Federal Grants, Foundations | Department of Parks and Recreation, Department of Mobility and Infrastructure
C4. The future of the Hill District will build upon and further emphasize the neighborhood’s African American cultural legacy and preservation. | Cultivate a community responsive to changing needs. The Hill District should be a resilient community that can adapt to various economic challenges while preserving its historic and cultural assets. | C4.3 | Adaptive reuse | Program | Identify historical buildings and sites that are suitable for adaptive reuse and develop a plan for incorporating sites into future development. These projects should strive to preserve and incorporate the Hill District’s unique character and cultural fabric. |  | X |  |  | None needed | Department of City Planning, Urban Redevelopment Authority
Community Welfare
C5. The relationship between law enforcement and community residents should be built on trust, cooperation, and effective communication. | Mitigate conflicts with law enforcement. Community trust should be built by reducing conflicts between law enforcement agencies and community members. | C5.1 | Community engagement with government departments | Partnership | Convene quarterly meetings between community and resident organizations and City of Pittsburgh departments to identify issues of wellbeing for Hill District Residents and establish a strategy to address them. |  |  |  | X | None needed | The Hill Registered Community Organizations, Community Based Organizations, Bureau of Police, Department of Public Safety
C5. The relationship between law enforcement and community residents should be built on trust, cooperation, and effective communication. | Mitigate conflicts with law enforcement. Community trust should be built by reducing conflicts between law enforcement agencies and community members. | C5.2 | Public assembly guide | Project | Create a public assembly and resource guide to reduce community and police conflict. The guide should provide best practices for organizing and managing events where large gatherings take place. This document should be created in conjunction with community members, law enforcement, and government agencies. |  | X |  |  | None needed | Department of Public Safety
C5. The relationship between law enforcement and community residents should be built on trust, cooperation, and effective communication. | Mitigate conflicts with law enforcement. Community trust should be built by reducing conflicts between law enforcement agencies and community members. | C5.3 | Hill District Crime Action Plan | Project | Develop a Hill District Violent Crime Action Plan that offers data-driven and culturally sensitive framework for reducing and preventing violent crimes. This should include collaboration between community members, law enforcement, and social service organizations. |  |  | X |  | Bureau of Police | The Hill Registered Community Organizations, Community Based Organizations, Bureau of Police
Public Art
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Incorporate cultural themes into public art. The public art in the Hill District is reflective of its cultural identity, historic legacy, and the progressive social-cultural landscape. | C6.1 | Cultural programming | Project | Develop a strategic approach to media and events that is aligned with past and current legacy of the Hill District (e.g., living legacy events). |  | X |  |  | None needed | The Hill Registered Community Organizations, Community Based Organizations
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Incorporate cultural themes into public art. The public art in the Hill District is reflective of its cultural identity, historic legacy, and the progressive social-cultural landscape. | C6.2 | Cultural and artistic markers | Project | Install signage, wayfinding, art, and exhibits that emphasize the Hill District’s historical significance. |  | X |  |  | State and Federal Grants | Department of Mobility and Infrastructure
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Incorporate cultural themes into public art. The public art in the Hill District is reflective of its cultural identity, historic legacy, and the progressive social-cultural landscape. | C6.3 | Graphic identity | Project | Create a graphic identity to foster community pride, attract local tourism, and ensure consistent clear and cohesive messaging regarding the Hill District. |  |  | X |  | State and Federal Grants, Philanthropy | The Hill Registered Community Organizations, Community Based Organizations
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Foster economic opportunities for creative businesses. Creative communities and businesses should have opportunities to grow and expand in the Hill District. | C6.4 | Funding for the arts | Project | Establish funding opportunities for the Hill District Arts Collective to support existing artists and creatives communities |  |  |  | X | Urban Redevelopment Authority, State and Federal Grants, Philanthropy | Department of City Planning
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Foster economic opportunities for creative businesses. Creative communities and businesses should have opportunities to grow and expand in the Hill District. | C6.5 | Hill Distrct Cultural Business Program | Program | Launch a Hill District Cultural Business Program in support of local and cultural businesses. A Hill District Business Program would provide capital and programmatic support for legacy, local, and culturally relevant businesses and organizations |  |  | X |  | Urban Redevelopment Authority, State and Federal Grants, Philanthropy | Urban Redevelopment Authority
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Foster economic opportunities for creative businesses. Creative communities and businesses should have opportunities to grow and expand in the Hill District. | C6.6 | Main Streets Program | Project | The Hill District has multiple corridors that could benefit from joining the national Main Streets Program to focus on providing technical assistance to historic businesses. |  |  | X |  | None needed | Department of Mobility and Infrastructure, Pittsburgh Regional Transit
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Strengthen community identity. The history of the Hill District should be preserved through placekeeping and community engagement. | C6.7 | Hill District History/Cultural Legacy Center | Project | Establish a Hill District History/Cultural Legacy Center to preserve the Hill’s legacy, encourage multi-generational engagement, and bring visitors to the Hill. |  |  | X |  | State and Federal Grants, Philanthropy | The Hill Registered Community Organizations, Community Based Organizations
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Strengthen community identity. The history of the Hill District should be preserved through placekeeping and community engagement. | C6.8 | Hill District Cultural and Historic Preservation Plan | Project | Create a Hill District Cultural and Historic Preservation Plan that would include an evaluation of existing historic and culturally significant resources as well as a variety of strategies for maintaining and enhancing those resources. |  |  | X |  | State and Federal Grants | Department of City Planning
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Tie public art to the history of the Hill District. The public art in the Hill District should be reflective of its cultural identity and cultural legacy | C6.9 | Formal engagement framework for public art | Partnership | Engage with community members to establish a selection process for local artists and secure funding and resources for public art installations. |  | X |  |  | None needed | Department of City Planning, Department of Parks and Recreation
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Tie public art to the history of the Hill District. The public art in the Hill District should be reflective of its cultural identity and cultural legacy | C6.10 | Local arts programming | Program | The City and community organizations should incorporate multiple strategies to promote arts programming including murals and public art, cultural festivals, workshops and classes, and public performances. |  |  |  | X | State and Federal Grants, Philanthropy | Department of City Planning, Department of Parks and Recreation
C6. Public art in the Hill District should be reflective of the community’s cultural identity and foster individual expression and while fostering economic development opportunities. | Tie public art to the history of the Hill District. The public art in the Hill District should be reflective of its cultural identity and cultural legacy | C6.11 | Cultural legacy walking tours | Program | Support and formalize existing cultural legacy walking tours in the Hill District and the Cultural Loop. |  |  |  | X | Philanthropy | The Hill Registered Community Organizations, Community Based Organizations
Public Health
C7. Positive health outcomes are promoted in the Hill District by providing healthy food buying/access options for residents and targeted interventions to reduce chronic illnesses. | Promote healthy and nutritional eating lifestyles. The Hill District is committed to creating an environment that supports healthy and nutritional eating lifestyles. | C7.1 | Food sovereignty | Program | Support and build upon existing urban agriculture within the Hill District to provide food sovereignty. |  |  |  | X | State and Federal Grants | Department of City Planning
C7. Positive health outcomes are promoted in the Hill District by providing healthy food buying/access options for residents and targeted interventions to reduce chronic illnesses. | Promote healthy and nutritional eating lifestyles. The Hill District is committed to creating an environment that supports healthy and nutritional eating lifestyles. | C7.2 | Healthy cooking club | Project | Create a healthy cooking club for parents and students to learn about healthy eating, and partner with local grocers and restaurants to host cooking demonstrations. |  | X |  |  | State and Federal Grants, Educational Institutions | The Hill Registered Community Organizations, Community Based Organizations
C7. Positive health outcomes are promoted in the Hill District by providing healthy food buying/access options for residents and targeted interventions to reduce chronic illnesses. | Promote healthy and nutritional eating lifestyles. The Hill District is committed to creating an environment that supports healthy and nutritional eating lifestyles. | C7.3 | Food access working group | Partnership | Form a food access working group to facilitate the creation of a food cooperative or buying club in the Hill District. |  | X |  |  | State and Federal Grants, Philanthropy | The Hill Registered Community Organizations, Community Based Organizations
C7. Positive health outcomes are promoted in the Hill District by providing healthy food buying/access options for residents and targeted interventions to reduce chronic illnesses. | Promote healthy and nutritional eating lifestyles. The Hill District is committed to creating an environment that supports healthy and nutritional eating lifestyles. | C7.4 | Farmers markets | Program | Promote an increase in farmers markets in the Hill District. | X |  |  |  | State and Federal Grants, Philanthropy | The Hill Registered Community Organizations, Community Based Organizations, Food Vendors
C7. Positive health outcomes are promoted in the Hill District by providing healthy food buying/access options for residents and targeted interventions to reduce chronic illnesses. | Reduce healthcare disparities. Health initiatives should prioritize reducing disparities in healthcare and chronic illnesses, with a particular focus on asthma and mental health. | C7.5 | Asthma education and awareness | Program | Establish management and support system for an asthma-friendly Hill District and provide asthma education and awareness programs for residents. |  |  |  | X | None needed | Allegheny County Health Department
C7. Positive health outcomes are promoted in the Hill District by providing healthy food buying/access options for residents and targeted interventions to reduce chronic illnesses. | Reduce healthcare disparities. Health initiatives should prioritize reducing disparities in healthcare and chronic illnesses, with a particular focus on asthma and mental health. | C7.6 | School-based harm reduction | Program | Provide community and school-based harm-reduction programs for mental health and substance abuse issues. |  |  |  | X | State and Federal Grants, Philanthropy | Community Based Organizations, Pittsburgh School District
Schools and Related Programs
C8. Educational outcomes should be improved through strong community partnerships and investments in resources that create an environment that values and promotes lifelong learning. | Create comprehensive engagement in education programming. Develop comprehensive education programs that actively engage students, families, and the community in the curriculum of local schools. | C8.1 | Hill District talent retention | Program | Establish partnerships with educational institutions, corporations and other organizations to improve Hill District students’ quality of education and engagement to aid in the pipeline of retaining diverse talent within the City of Pittsburgh. |  |  | X |  | Educational institutions | Pittsburgh School District
C8. Educational outcomes should be improved through strong community partnerships and investments in resources that create an environment that values and promotes lifelong learning. | Create comprehensive engagement in education programming. Develop comprehensive education programs that actively engage students, families, and the community in the curriculum of local schools. | C8.2 | Hill District cultural legacy curriculum | Program | Develop and implement a Hill District Cultural Legacy curriculum. |  |  |  | X | State and Federal Grants, Educational Institutions | Pittsburgh School District
C8. Educational outcomes should be improved through strong community partnerships and investments in resources that create an environment that values and promotes lifelong learning. | Create comprehensive engagement in education programming. Develop comprehensive education programs that actively engage students, families, and the community in the curriculum of local schools. | C8.3 | After-school programs | Program | Catalogue, advertise, and improve access to after-school programs and create opportunities such as fundraisers to support local organizations and help them grow in capacity. |  |  |  | X | Educational institutions | Pittsburgh School District, The Hill Registered Community Organizations, Community Based Organizations,

## Mobility Matrix
Goal | Policy | ID | Strategy | PPP | Detail | Timeline |  |  |  | Funding Source | Implementors
[6 empty] | 0-2 | 3-5 | 6-10 | Ongoing
Transit Service and Stations
M1. Transit connections to surrounding areas, accessibility, affordability, and efficiency are prioritized to strengthen transit’s role in overcoming systemic inequities. | Support well-informed decision-making. Decisions about public transit service should incorporate data-driven approaches to equity that are clearly communicated to and understandable by the public. | M1.1 | PRT Bus Line Redesign audit | Project | Conduct a thorough review of the effectiveness of the PRT Bus Line Redesign and recommend potential changes based on data collection and community feedback. |  | X |  |  | None needed | Pittsburgh Regional Transit, Mobility and Infrastructure, Hill District RCOs
M1. Transit connections to surrounding areas, accessibility, affordability, and efficiency are prioritized to strengthen transit’s role in overcoming systemic inequities. | Facilitate equitable access to public transit. Through a combination of public and private initiatives and outreach efforts, residents, employees, and visitors should access public transit services, regardless of their income level. | M1.2 | Discount transit passes | Program | Create a program that allows employers, developers, and other organizations to make transit pass purchases at a discount. |  |  |  | X | Major Employers | Pittsburgh Regional Transit, Hill District RCOs, Major employers
M1. Transit connections to surrounding areas, accessibility, affordability, and efficiency are prioritized to strengthen transit’s role in overcoming systemic inequities. | Improve neighborhood connections to public transit. All people are within a five-minute walk or roll of local transit service and/or a 10-minute non-auto connection to rapid transit service. Topography, rider age, and other relevant factors are considered as part of improving access. | M1.3 | Transit Connections | Program | Implement PRT's NEXTransit Project G, connecting the Hill District with the Strip District, Oakland, Hazelwood, and Carrick through new public transit service. |  |  | X |  | Pittsburgh Regional Transit | Department of Mobility and Infrastructure, Department of City Planning
M1. Transit connections to surrounding areas, accessibility, affordability, and efficiency are prioritized to strengthen transit’s role in overcoming systemic inequities. | Reduce single-occupant vehicle trips. All employers, venues, and attractions use transportation demand management practices to reduce single-occupant vehicle trips and associated impacts, such as incentivizing the use of public transit, walking, cycling, and carpooling. | M1.4 | Transportation demand management program | Partnership | Develop a comprehensive strategy that brings together all relevant agencies, institutions, and non-profit partners to reduce single-occupancy vehicle trips and congestion in the Hill District. This should include incentives programs at institutions and major employers, updated City policies and regulations for development, a program to more efficiently utilize existing parking facilities, and informational campaigns for those coming into the Hill District as well as new and existing residents. | X |  |  |  | Congestion Mitigation and Air Quality Improvement Program (CMAQ), Pittsburgh Regional Transit | Pittsburgh Regional Transit, Department of Mobility and Infrastructure, Major Employers, Pittsburgh City Council, Hill District RCOs
M2. Transit stops and station areas are attractive hubs of activity and buses provide the safest, most comfortable, and enjoyable way to get where you’re going. | Expand amenities at transit stops. Ensure well-used bus stops have appropriate amenities for riders and meet PRT design guidelines for safety and accessibility. | M2.1 | Improve the transit rider experience. | Program | Improve transit users’ access, comfort and mobility when taking transit by including weather protection, lighting, art, green features, signage, bike parking, and safe multimodal connections, in addition to minimum bus stop features, where appropriate, based on prioritization criteria. Ensure that bus stops are accessible via well-marked crosswalks and well-maintained sidewalks. |  |  |  | X | State and Federal Grants, Foundation Grants, Pittsburgh Regional Transit | Pittsburgh Regional Transit, Department of Mobility and Infrastructure, Hill District RCOs
M2. Transit stops and station areas are attractive hubs of activity and buses provide the safest, most comfortable, and enjoyable way to get where you’re going. | Expand amenities at transit stops. Ensure well-used bus stops have appropriate amenities for riders and meet PRT design guidelines for safety and accessibility. | M2.2 | Safe and accessible bus stops | Project | All bus stops meet PRT design guidelines for safety and accessibility. Additional amenities above the guidelines are incorporated at well-used bus stops. |  |  |  | X | Pittsburgh Regional Transit | Pittsburgh Regional Transit, Department of Mobility and Infrastructure
Pedestrian Access, Safety, and Circulation
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Create spaces for community activities. Repurpose portions of streets and intersections to create plazas and open space for community activities, mobility hubs, green infrastructure, leisure, and commerce. | M3.1 | Mobility hub at Chauncey and Centre | Project | Widen the sidewalk at Chauncey and Centre and add a mobility hub. Explore the possible conversion of the parking area to green infrastructure and/or to a public plaza space. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Pittsburgh Regional Transit, Department of Mobility and Infrastructure, Department of City Planning, Micro-mobility companies
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Create spaces for community activities. Repurpose portions of streets and intersections to create plazas and open space for community activities, mobility hubs, green infrastructure, leisure, and commerce. | M3.2 | Play streets | Project | Coordinate with Citiparks to create "play streets" as temporary open spaces for youth to play and socialize. A play street occurs on a local street that is closed to traffic for specific hours on a regular basis. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure, CitiParks, Department of Public Works, Department of City Planning, Hill District RCOs, Pittsburgh Public Schools
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Create spaces for community activities. Repurpose portions of streets and intersections to create plazas and open space for community activities, mobility hubs, green infrastructure, leisure, and commerce. | M3.3 | Chauncey shared street | Project | Create a shared street on Chauncey Street from Webster Avenue to Bedford Avenue. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure. Hill District RCOs
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Enhance pedestrian infrastructure. Ensure pedestrian access in the right of way to all residences, businesses, and other destinations. Work with property owners and other agencies to prioritize pedestrian improvements that meet residents' travel needs and patterns. | M3.4 | Accountable maintenance of pedestrian infrastructure | Program | Develop policy and educate staff at the Department of Mobility and Infrastructure, Permit, Licensing, and Inspections and 311 to improve enforcement of sidewalk conditions for large commercial property owners. |  |  |  | X | None needed | Department of Mobility and Infrastructure, Permit, Licenses, and Inspections Department, 311
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Create safe sidewalks. Sidewalks are appropriately sized, complete, maintained, and clear of obstructions. | M3.5 | Prioritize removal of obstructions | Project | Identify and rank pedestrian route segments for snow removal. Coordinate City crews with volunteers and homeowners to clear during weather events. | X |  |  |  | State and Federal Grant Funding, Capital Budget | Department of Public Works, Hill District RCOs, Property Owners
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Create safe sidewalks. Sidewalks are appropriately sized, complete, maintained, and clear of obstructions. | M3.6 | Sidewalk repair program | Program | Study the creation of a program that efficiently addresses urgent sidewalk repairs, with a minimum cost burden to qualifying homeowners and property owners. |  | X |  |  | State and Federal Grants | Department of Public Works, Department of Mobility and Infrastructure, Hill District RCOs, Property Owners, Mayor's Office, Permits, Licensing, and Inspections, 311
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Increase safety and accessibility along pedestrian routes. Pedestrian routes offer safe, convenient, seamless, and accessible travel connections to key destinations. | M3.7 | Kennard pedestrian connection | Project | Create a pedestrian connection from the dead end on Reed Street down to the intersection of Reed and Kirkpatrick. Explore additional trail connections down Kirkpatrick. |  | X |  |  | State and Federal Grant Funding, Capital Budget | CitiParks, Hill District RCOs, Department of Mobility and Infrastructure, Department of Public Works, Department of City Planning, Property Owners
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Increase safety and accessibility along pedestrian routes. Pedestrian routes offer safe, convenient, seamless, and accessible travel connections to key destinations. | M3.8 | Kirkpatric and Reed intersection improvements | Project | Install pedestrian and traffic safety improvements at the intersection of Kirkpatrick and Reed. Study converting Kennard Playground's parking lot to green space, a mobility hub, and relocating parking elsewhere. |  | X |  |  | State and Federal Grant Funding, Capital Budget | CitiParks, Department of Public Works, Pittsburgh Bike Share, Micro-mobility companies
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Increase safety and accessibility along pedestrian routes. Pedestrian routes offer safe, convenient, seamless, and accessible travel connections to key destinations. | M3.9 | Lighting improvements | Project | Inventory, rank and install lighting improvements to improve safety. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure, Hill District RCOs, Department of City Planning
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Increase safety and accessibility along pedestrian routes. Pedestrian routes offer safe, convenient, seamless, and accessible travel connections to key destinations. | M3.10 | Coal Seam Trail | Project | Use the Coal Seam Trail to create a connected network of green spaces along the northern ridge. Provide public access between Bedford Avenue and the trail at strategic locations. Explore the potential to make this trail a shared use path for both pedestrians and cyclists. |  |  | X |  | State and Federal Grant Funding, Capital Budget | Department of City Planning, Department of Mobility and Infrastructure, Parks Conservancy
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Create a seamless network of connected sidewalks. Sidewalks form an interconnected network that provide pedestrians multiple options to reach their destinations despite steep slopes or other obstacles. | M3.11 | Sidewalk Inventory Program | Program | Create a program to inventory, rank, and install sidewalk and accessibility improvements and remove pedestrian obstructions. Coordinate with residents, stakeholders, and the disability community. | X |  |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure, Department of Public Works, Hill District RCOs, Property Owners, Disability-Led Organizations
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Create a seamless network of connected sidewalks. Sidewalks form an interconnected network that provide pedestrians multiple options to reach their destinations despite steep slopes or other obstacles. | M3.12 | Chauncey Street sidewalk improvements | Project | Fill in sidewalk gaps on Chauncey Street between Mahon Street and Webster Street. | X |  |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure, Housing Authority for the City of Pittsburgh, Hill District RCOs
M3. The Hill District should be a walkable neighborhood where pedestrians can reach destinations conveniently, comfortably, and safely, while enjoying streetscapes that support social interaction. | Prioritize the maintenance of public owned steps. The City's publicly owned steps are regularly monitored, maintained, and repaired, and are designed to accommodate bicycles. | M3.13 | Chauncey Street Public Steps improvements | Project | Complete the reconstruction and improve the Chauncey Street Steps as outlined in the Bedford Dwellings Transformation Plan. | X |  |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure, Housing Authority for the City of Pittsburgh, Hill District RCOs
Accessibility
M4. The Hill District's mobility network and its built environment are accessible to people of all ages, abilities, races, and income levels. | Prioritize ADA improvements. Collaborate with residents and the disability community to identify and implement priority ADA improvements along sidewalks and streetscapes. In cases where topography precludes full compliance, design to maximize accessibility. | M4.1 | Transportation advocacy | Partnership | Identify a local community-based group or organization or collective of residents to champion mobility improvements throughout the Hill District and support implementation of proposed projects, programs, and policies. | X |  |  |  | State and Federal Grant Funding, Foundation Funding | Department of Mobility and Infrastructure, Department of City Planning, Hill District RCOs
M4. The Hill District's mobility network and its built environment are accessible to people of all ages, abilities, races, and income levels. | Prioritize ADA improvements. Collaborate with residents and the disability community to identify and implement priority ADA improvements along sidewalks and streetscapes. In cases where topography precludes full compliance, design to maximize accessibility. | M4.2 | Dedicated disability parking space expansion | Program | As a part a of larger neighborhood-wide parking program, convert existing spaces to accessible parking in high demand areas. |  |  | X |  | State and Federal Grant Funding | Department of Mobility and Infrastructure, Department of City Planning
M4. The Hill District's mobility network and its built environment are accessible to people of all ages, abilities, races, and income levels. | Expand digital access to improve mobility services. Work with Move PGH and others to expand residents' digital access to mobility services and trip planning information. Reduce barriers to accessing such services. | M4.3 | Hill District travel data collection | Program | Periodically collect data on Hill District travel patterns to guide decision-making on public and private investments regarding mobility. Data is disaggregated by key demographic indicators, including race, income, age, ability, and more. |  |  |  | X | None needed | Department of Mobility and Infrastructure, Department of Innovation and Perfrormance, Mobilify
M4. The Hill District's mobility network and its built environment are accessible to people of all ages, abilities, races, and income levels. | Reduce barriers to mobility modes. Design mobility programs and mobility projects to minimize barriers of access to different mobility modes. | M4.4 | Mobility rituals | Program | Consider starting or restarting community mobility rituals and recreational activities in the Hill District. |  |  |  | X | State and Federal Grant Funding | Hill District RCOs, YMCA, Pittsburgh Bike Share
M4. The Hill District's mobility network and its built environment are accessible to people of all ages, abilities, races, and income levels. | Reduce barriers to mobility modes. Design mobility programs and mobility projects to minimize barriers of access to different mobility modes. | M4.5 | Micro-mobility access | Project | Install micro-mobility hubs and charging stations, taking into consideration factors such as bus stops, topography, one-way trips, and community input. Ensure the micro-mobility equipment is accessible to all users and implement discount and alternative payment programs to reduce participation barriers. Additionally, enhance unbiased, reward-based enforcement mechanisms to improve compliance with scooter parking requirements. |  |  | X |  | State and Federal Grants, Move PGH | Department of Mobility and Infrastructure, Move PGH, Private transportation companies, Department of City Planning, Hill District RCOs
Traffic Safety
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Mitigate traffic safety risks. Traffic calming and safety improvements are implemented in corridors and intersections with high volumes or speeds and where traffic safety risks are posed. | M5.1 | Engineering study | Project | Conduct an engineering study to determine the feasibility of realigning the Centre/Dinwiddie/Devilliers intersection and closing the south block of Devilliers. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure, Department of Public Works, Department of City Planning, Pittsburgh Bike Share, Micro-mobility companies, Hill District RCOs
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Mitigate traffic safety risks. Traffic calming and safety improvements are implemented in corridors and intersections with high volumes or speeds and where traffic safety risks are posed. | M5.2 | Safety improvements along Centre and Kirkpatrick | Project | Convert Centre and Kirkpatrick to a four-way intersection. Close Mahon Street from Centre Avenue and convert part of Mahon Street to a pedestrian plaza. Install intersection safety improvements. | X |  |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure, Department of Public Works, Department of City Planning, Pittsburgh Bike Share, Micro-mobility companies, Hill District RCOs
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Mitigate traffic safety risks. Traffic calming and safety improvements are implemented in corridors and intersections with high volumes or speeds and where traffic safety risks are posed. | M5.3 | Traffic calming improvements | Project | Through the Rebuilding American Infrastructure with Sustainability and Equity (RAISE) grant, install traffic calming treatments, reconstruct intersections, and improve city steps in areas that pose traffic safety risks, per DOMI prioritization criteria. These locations should include: • Centre Ave between Dinwiddie and Kirkpatrick Street • Bedford Ave • Crawford Street and Pride Street • Dinwiddie Street • Webster Street |  |  |  | X | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure, Department of Public Works, Department of City Planning, Hill District RCOs
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Mitigate traffic safety risks. Traffic calming and safety improvements are implemented in corridors and intersections with high volumes or speeds and where traffic safety risks are posed. | M5.4 | Modernize traffic signals | Project | Complete the implementation of the SmartSpines project in the Hill District to modernize traffic signals along Centre Avenue and Bigelow Boulevard. |  | X |  |  | State and Federal Grants | Department of Mobility and Infrastructure
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Mitigate traffic safety risks. Traffic calming and safety improvements are implemented in corridors and intersections with high volumes or speeds and where traffic safety risks are posed. | M5.5 | Traffic congestion management | Program | Establish a coordination program with partners for managing traffic congestion during major events. Focus on maintaining bus service and accessibility to meet residents' mobility needs. | X |  |  |  | None needed | Department of Mobility and Infrastructure, Department of City Planning, Permits, Licensing, and Inspections, Hill District RCOs, Department of Public Works, Office of Special Events
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Mitigate traffic safety risks. Traffic calming and safety improvements are implemented in corridors and intersections with high volumes or speeds and where traffic safety risks are posed. | M5.6 | Safety improvements along Reed Street and Centre Avenue | Project | Realign the intersection of Reed Street and Centre Avenue to improve safety for all users. |  |  | X |  | State and Federal Grants, Pittsburgh Regional Transit | Department of Mobility and Infrastructure, Department of Public Works, Department of City Planning, Pittsburgh Bike Share, Micro-mobility companies, Hill District RCOs
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Mitigate traffic safety risks. Traffic calming and safety improvements are implemented in corridors and intersections with high volumes or speeds and where traffic safety risks are posed. | M5.7 | Construction coordination program | Program | Establish a construction coordination program that connects public agencies with community stakeholder organizations to maintain a list of projects and anticipated construction schedules. |  |  | X |  | None needed | Department of Mobility and Infrastructure, Department of City Planning, Permits, Licensing, and Inspections, Hill District RCOs, Department of Public Works, Office of Special Events
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Design streetscapes for the pedestrian scale. Streetscapes are designed for the pedestrian scale, incorporating lighting, street furniture, landscaping and elements that make streets a comfortable and attractive pedestrian environment. | M5.8 | Streetscape improvements along Centre Avenue | Project | Install streetscape improvements along Centre Ave. that enhance safety for all users, improve the pedestrian experience, and manage parking. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Department of City Planning, Department of Public Works, Pittsburgh Bike Share, Micro-mobility Companies, Hill District RCOs
M5. There are zero traffic fatalities and no serious injuries due to traffic in the Hill District. | Design streetscapes for the pedestrian scale. Streetscapes are designed for the pedestrian scale, incorporating lighting, street furniture, landscaping and elements that make streets a comfortable and attractive pedestrian environment. | M5.9 | Centre Avenue traffic calming and streetscape study | Project | Study opportunities to calm traffic and improve the streetscape along Centre Ave between Dinwiddie and Roberts Street as part of Centre/Heldman activation. Possibilities include distinctive paving, public art, and other urban design approaches to activate the public realm in a way that reflects the living cultural legacy of the Hill District. Consider studying improvements on Centre Ave west of Roberts Street if warranted by pedestrian safety considerations. In addition, study ways to improve the streetscape, sidewalk conditions and pedestrian safety along Centre Ave between Kirkpatrick and Reed Streets. | X |  |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobilty and Infrastructure, Department of City Planning, Urban Redevelopment Authority, Hill District RCOs
Parking
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Optimize on-street parking. On-street parking should be managed efficiently to ensure balanced usage and sufficient availability of spaces. | M6.1 | Parking study | Project | Explore a proposed scope of work for a parking study. The study could examine the number of off-street and on-street parking spaces needed to meet current and projected parking demand based on anticipated future developments. It could also consider case studies, opportunities and tools to address the Hill District’s parking challenges in ways that account for the Hill District’s context, including its mobility network and topography, and it could consider evaluating costs and trade-offs between available alternatives. | X |  |  |  | State and Federal Grant Funding, Capital Budget | City Council, Hill District RCOs, Department of Mobility and Infrastructure, Pittsburgh Regional Transit
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Optimize on-street parking. On-street parking should be managed efficiently to ensure balanced usage and sufficient availability of spaces. | M6.2 | Parking meter installation | Project | Install parking meters along Centre Avenue from Dinwiddie Street to Reed Street. Consider providing residential parking permit zones on side streets to minimize spillover parking on residential streets. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Pittsburgh Parking Authority, Department of Mobility and Infrastructure, Department of City Planning, Hill District RCOs
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Optimize on-street parking. On-street parking should be managed efficiently to ensure balanced usage and sufficient availability of spaces. | M6.3 | Demand-based pricing | Program | Use pricing at on-street and off-street parking sites to guide users towards the most appropriate parking for their needs. |  |  | X |  | Pittsburgh Regional Transit, Department of Mobility and Infrastructure | Pittsburgh Regional Transit, Department of Mobility and Infrastructure
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Expand access to off-street parking. Off-street parking options should allow for sharing of existing parking resources. Provide off-street parking based on demand and funding. | M6.4 | New parking resources | Project | Increase available off-street parking resources, construct temporary parking on vacant lots that serve parking needs for the near-term but which can be converted to other uses in the long-term based on the Hill District's development and needs. |  |  |  | X | State and Federal Grant Funding, Capital Budget | Department of Mobilty and Infrastructure, Department of City Planning, Hill District RCOs
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Expand access to off-street parking. Off-street parking options should allow for sharing of existing parking resources. Provide off-street parking based on demand and funding. | M6.5 | Parking sharing agreements | Program | Optimize existing off-street parking resources, identify possible locations for parking sharing agreements for land uses that have different parking demands throughout the week. | X |  |  |  | None needed | Hill District RCOs, Urban Redevelopment Authority, Property Owners
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Streamlining parking in residential neighborhoods. Adjust the Residential Parking Permit Program (RPP) as development pressure changes throughout the neighborhood. | M6.6 | Parking Enhancement District | Program | Expand the RPP zones in the Hill District, establish a Parking Enhancement District (PED), and provide resources to cut barriers to access. | X |  |  |  | None needed | City Council, Department of Mobility and Infrastructure, Pittsburgh Parking Authority, Department of City Planning, Hill District RCOs
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Streamlining parking in residential neighborhoods. Adjust the Residential Parking Permit Program (RPP) as development pressure changes throughout the neighborhood. | M6.7 | Contextual Parking Program | Program | Modify the RPP program, PED program, and off-street parking zoning standards to allow parking programs to be tailored to the Hill District context. | X |  |  |  | None needed | Mayor's Office, City Council, Department of Mobility and Infrastructure, Pittsburgh Parking Authority, Department of City Planning, Hill District RCOs
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Create a structure of unbiased parking enforcement. Promote compliance with parking regulations while respecting the rights and needs of all community members. | M6.8 | Community informed parking enforcement approach | Program | Parking enforcement should be guided by the needs of residents and visitors to the Hill District. Parking regulations should be user-friendly and include education along with enforcement. |  |  |  | X | None needed | Pittsburgh Parking Authority, Hill District RCOs, Department of Mobility and Infrastructure
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Create a structure of unbiased parking enforcement. Promote compliance with parking regulations while respecting the rights and needs of all community members. | M6.9 | Automated parking enforcement | Project | Explore the potential for using automated parking enforcement as technologies are developed and permitted. |  |  |  | X | None needed | Department of Mobility and Infrastructure
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Efficiently manage curbside spaces. Manage curbside space to provide for deliveries, pickup and drop-off, short-term loading, bike+ uses, and other needs. | M6.10 | Curbside management program | Program | Create a curbside management program to improve the mobility, safety, and livability of the community through the proactive planning and use of curb space throughout the Hill District. | X |  |  |  | State and Federal Grant Funding, Capital Budget | Parking Authority Magisterial District Court for Allegheny Councy, Hill District RCOs
M6. On- and off-street parking is continuously managed as a system to meet the needs of existing and future residents, businesses, and visitors with sufficient but not excessive amounts at appropriate locations while not impeding the growth, vitality, and health of the neighborhood. | Efficiently manage curbside spaces. Manage curbside space to provide for deliveries, pickup and drop-off, short-term loading, bike+ uses, and other needs. | M6.11 | Curbside extensions | Program | Install curb extensions to protect the curbside space from illegal behavior. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobility and Infrastructure
M7. Development projects are designed to minimize negative traffic and parking impacts on existing and future residents. | Minimize noise and pollution in new development. Traffic and parking plans of Hill District development projects should minimize noise and pollution impacts on existing and future neighborhood residents, while maximizing resident access to parking and the public right of way leading to their homes. | M7.1 | Privately funded mobility infrastructure | Program | Examine opportunities for the development review process to work with developers to increase pedestrian, bicycle, and public transit access, support community uses in the right of way, reduce curb cuts, site bike share and mobility hubs at new developments, and more. |  |  |  | X | None needed | Department of City Planning, Department of Mobility and Infrastructure, Permits, Licensing, and Inspections, Hill District RCOs
Bike Infrastructure
M8. The Hill District is a safe and connected place where residents can travel within the Hill District and to nearby neighborhoods by bicycle or other means of micromobility. Bicycle infrastructure and activities reflect the Hill District context, topography, and culture. | Identify suitable bicycle facilities. Build community consensus around what bicycle facilities are desired in the Hill District. | M8.1 | Implement the Bike (+) Plan | Program | Build on the Bike (+) Plan's recommendations for installing bicycle facilities on Herron Ave from the northern segment of Bigelow Blvd to Wylie Ave, and explore the installation of bicycle facilities along Herron Ave and Centre Ave between Wylie and the southern segment of Bigelow Blvd. Implement traffic calming measures along Herron Ave from the northern segment of Bigelow Blvd to Centre Ave. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobilty and Infrastructure, Department of City Planning, Department of Public Works, Pittsburgh Bike Share, Micro-mobility companies, Hill District RCOs
M8. The Hill District is a safe and connected place where residents can travel within the Hill District and to nearby neighborhoods by bicycle or other means of micromobility. Bicycle infrastructure and activities reflect the Hill District context, topography, and culture. | Identify suitable bicycle facilities. Build community consensus around what bicycle facilities are desired in the Hill District. | M8.2 | Bicycle facilities on Kirkpatrick Street | Project | Engage the community on the design of bicycle facilities on Kirkpatrick between Reed Street and Fifth Ave. Use traffic calming elements to slow down traffic and improve pedestrian access. | X |  |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobilty and Infrastructure, Department of City Planning, Department of Public Works, Pittsburgh Bike Share, Micro-mobility companies, Hill District RCOs
M8. The Hill District is a safe and connected place where residents can travel within the Hill District and to nearby neighborhoods by bicycle or other means of micromobility. Bicycle infrastructure and activities reflect the Hill District context, topography, and culture. | Collaborate to improve the bike network. Work with the community to create a safe, connected, and accessible network that serves users traveling within the neighborhood and connecting to other neighborhoods. | M8.3 | Wylie Avenue improvements | Project | Convert Wylie Avenue to a neighborway that prioritizes pedestrians, bicyclists, and other non-vehicular traffic. Install traffic calming elements to slow down traffic and improve pedestrian and bicycle access. |  | X |  |  | State and Federal Grant Funding, Capital Budget | Department of Mobilty and Infrastructure, Hill District RCOs
M8. The Hill District is a safe and connected place where residents can travel within the Hill District and to nearby neighborhoods by bicycle or other means of micromobility. Bicycle infrastructure and activities reflect the Hill District context, topography, and culture. | Expand access to bike share stations and mobility hubs. Work with the community and other partners to site bike share stations and mobility hubs. Make sure that sites are close to public transit stops and account for users' one-way trips. Work with partners to provide enough Bike Share infrastructure to accommodate neighborhood demand. | M8.4 | Bicycle supportive infrastructure | Program | Install infrastructure that supports bicycling, including bicycle racks, bicycle parking, and other more. |  |  |  | X | State and Federal Grant Funding, Capital Budget | Pittsburgh Regional Transit , Department of Mobilty and Infrastructure, Developers, Hill District RCOs, Bike PGH
M8. The Hill District is a safe and connected place where residents can travel within the Hill District and to nearby neighborhoods by bicycle or other means of micromobility. Bicycle infrastructure and activities reflect the Hill District context, topography, and culture. | Expand access to bike share stations and mobility hubs. Work with the community and other partners to site bike share stations and mobility hubs. Make sure that sites are close to public transit stops and account for users' one-way trips. Work with partners to provide enough Bike Share infrastructure to accommodate neighborhood demand. | M8.5 | Bike share expansions | Program | Expand access to bike share stations and mobility hubs. Work with the community and other partners to site bike share stations and mobility hubs. Make sure that sites are close to public transit stops and account for users' one-way trips. Work with partners to provide enough bike share infrastructure to accommodate neighborhood demand. |  |  |  | X | Pittsburgh Regional Transit, State and Federal Grants | Pittsburgh Regional Transit , Department of Mobilty and Infrastructure, Pittsburgh Bike Share, Move PGH, InnovatePGH, Department of City Planning, Hill District RCOs

## Infrastructure Matrix
Goal | Policy | ID | Strategy | PPP | Detail | Timeline |  |  |  | Funding Source | Implementors
[6 empty] | 0-2 | 3-5 | 6-10 | Ongoing
Stormwater Management, Energy, Waste Mangement and Recycling, Digital Network and Utilities
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Prioritize efficient management of stormwater runoff. The City should manage stormwater runoff through responsible practices that enhance urban water cycles, support biodiversity, and protect public health and property. | I1.1 | Street level infrastructure investments | Project | Identify and make improvements on high-capture streets and alleys that can safely convey stormwater, improve pedestrian and bicycle safety, and add tree canopy through coordinated and intentional infrastructure. Projects should be in alignment with current stormwater code updates and include above ground green infrastructure where technically feasible. |  |  |  | X | Department of Public Works, Philanthropy, State and Federal Grants | Department of Public Works
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Prioritize efficient management of stormwater runoff. The City should manage stormwater runoff through responsible practices that enhance urban water cycles, support biodiversity, and protect public health and property. | I1.2 | Green stormwater infrastructure | Project | Amend the Hill District zoning districts to include existing incentives for stormwater management through green infrastructure. Support excellence in projects with additional resources and grants. |  | X |  |  | None needed | Department of City Planning, Department of Public Works
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Design eco-friendly initiatives. The Hill District community should adopt environmental practices that address climate change, promote sustainable development, and enhance the living conditions for all residents. | I1.3 | Sustainable building practices | Partnership | Engage with Hill District area organizations and developers about the Pennsylvania Commercial Property Assess Clean Energy Program (C-PACE) and other funding mechanisms to further embed high-performing and healthy building practices in commercial and multi-family projects. |  |  |  |  | None needed | Department of Public Works
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Design eco-friendly initiatives. The Hill District community should adopt environmental practices that address climate change, promote sustainable development, and enhance the living conditions for all residents. | I1.4 | Sustainable development policy guidelines | Project | Establish policy guidelines for sustainable development at different scales that aligns with the zoning and building code. |  | X |  |  | None needed | Department of City Planning, Department of Public Works
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Design eco-friendly initiatives. The Hill District community should adopt environmental practices that address climate change, promote sustainable development, and enhance the living conditions for all residents. | I1.5 | Clean Energy Plan | Project | Partnership organizations should prioritize the development of policies and programs to implement the Energy Action Plan developed in collaboration with Hill District Residents. | X |  |  |  | State and Federal Grants, Philanthropy | Department of Public Works, Department of City Planning
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Design eco-friendly initiatives. The Hill District community should adopt environmental practices that address climate change, promote sustainable development, and enhance the living conditions for all residents. | I1.6 | Energy generation on vacant land | Project | Identify potential projects for converting vacant land into energy generating uses through the use of grant money from the U.S. Department of Energy’s Communities Local Energy Action Program (LEAP). |  | X |  |  | Federal Grants | Department of Public Works, Department of City Planning
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Design eco-friendly initiatives. The Hill District community should adopt environmental practices that address climate change, promote sustainable development, and enhance the living conditions for all residents. | I1.7 | Zoning code amendments | Project | Amend the zoning code to address scale issues for smaller buildings and homes adjacent to larger structures to protect access to light and air needed for on-site renewables such as solar photovoltaics and wind turbines. |  | X |  |  | None needed | Department of City Planning
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Design eco-friendly initiatives. The Hill District community should adopt environmental practices that address climate change, promote sustainable development, and enhance the living conditions for all residents. | I1.8 | Sustainable home improvements | Project | Promote pathways for homeowners to improve their homes while addressing the climate crisis and air pollution. |  |  |  | X | State and Federal Grants, Philanthropy | Community Based Organizations, Department of Public Works
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Design eco-friendly initiatives. The Hill District community should adopt environmental practices that address climate change, promote sustainable development, and enhance the living conditions for all residents. | I1.9 | Litter reduction | Project | Add litter receptacles in strategic locations in accordance with resident feedback to reduce litter in Hill District neighborhoods. |  |  |  | X | State and Federal Grants, Philanthropy | Department of Public Works
I1. The Hill District's accessible infrastructure systems (utilities, food, digital, roads, stormwater) are high-yielding and resilient. | Upgrade digital network infrastructure. The Hill District should have a robust and inclusive digital network that supports economic development and educational opportunities. | I1.10 | Community service hubs | Project | Provide high speed internet access at community service hubs and build on workforce development programs such as Rec2Tech to increase to access to careers in innovation and technology-based fields |  |  | X |  | State and Federal Grants, Philanthropy | Department of Innovation and Performance, Department of Public Works
Open Space, Tree Canopy, Habitat Restoration, Urban Agriculture
I2. The Hill District contains a network of connected parks and green spaces in addition to integrated natural areas that prioritize a robust tree canopy and habitat restoration to foster environmental stewardship and social bonds. | Increase access to quality parks and open space. Open space in the Hill District should be maintained and expanded to ensure all residents have access to natural environments for recreation, relaxation, and ecological benefits. | I2.1 | Hill District Parks Plan implementation | Project | Prioritize improvements to existing park amenities as outlined in the Hill District Parks Plans. |  | X |  |  | State and Federal Grants, Philanthropy | Department of Parks and Recreation
I2. The Hill District contains a network of connected parks and green spaces in addition to integrated natural areas that prioritize a robust tree canopy and habitat restoration to foster environmental stewardship and social bonds. | Increase access to quality parks and open space. Open space in the Hill District should be maintained and expanded to ensure all residents have access to natural environments for recreation, relaxation, and ecological benefits. | I2.2 | Green public and underutilized spaces | Project | Identify and improve underutilized and vacant land such as parking lots and areas in the right of way that can provide environmental benefit such as native plant gardens. This strategy should incorporate community gardens to create a comprehensive greening strategy. |  |  |  | X | State and Federal Grants, Urban Redevelopment Authority | Department of City Planning, Urban Redevelopment Authority
I2. The Hill District contains a network of connected parks and green spaces in addition to integrated natural areas that prioritize a robust tree canopy and habitat restoration to foster environmental stewardship and social bonds. | Increase access to quality parks and open space. Open space in the Hill District should be maintained and expanded to ensure all residents have access to natural environments for recreation, relaxation, and ecological benefits. | I2.3 | Park and open space inventory | Project | Maintain an inventory of open spaces, their functions, and identified resident needs. This can be used to advocate for specific functions and design features with public and private investments in open space. |  |  |  | X | None needed | Department of Parks and Recreation
I2. The Hill District contains a network of connected parks and green spaces in addition to integrated natural areas that prioritize a robust tree canopy and habitat restoration to foster environmental stewardship and social bonds. | Preserve and expand tree canopy. The tree canopy in the Hill District should be preserved and expanded to improve air quality, enhance biodiversity, and promote health and well-being, including helping to prevent heat-related health complications. | I2.4 | Greenway expansion | Project | Prioritize projects such as the Colwell Trail and the Coal Seam Trail that incorporate tree retention, hillside stabilization, and habitat restorations, while allowing for preservation of views and programming opportunities. |  | X |  |  | State and Federal Grants, Urban Redevelopment Authority | Department of Parks and Recreation, Department of City Planning
I2. The Hill District contains a network of connected parks and green spaces in addition to integrated natural areas that prioritize a robust tree canopy and habitat restoration to foster environmental stewardship and social bonds. | Preserve and expand tree canopy. The tree canopy in the Hill District should be preserved and expanded to improve air quality, enhance biodiversity, and promote health and well-being, including helping to prevent heat-related health complications. | I2.5 | Comprehensive tree canopy plan | Program | Build on the work of citywide and local non-profits to create a cohesive neighborhood-wide tree canopy strategy that recognizes trees as vital and cost-effective infrastructure. This should include preserving existing trees in planned development, funding and planting new trees in alignment with the Greenprint Plan, and maintaining trees along streets, on private property, and in open spaces. |  |  |  | X | State and Federal Grants, Urban Redevelopment Authority | Department of Parks and Recreation, Department of City Planning
I2. The Hill District contains a network of connected parks and green spaces in addition to integrated natural areas that prioritize a robust tree canopy and habitat restoration to foster environmental stewardship and social bonds. | Restore and maintain natural habitats. The City should strive to restore and maintain natural habitats in the Hill District through strategic planning, contextual development regulations, and community engagement. | I2.6 | Hillside land use management | Project | Establish a comprehensive land use and environmental management approach to hillsides, especially in landslide prone areas and undermined areas that focus on invasive species management, stabilization, restoration, and long-term maintenance. |  |  | X |  | None needed | Department of City Planning
I2. The Hill District contains a network of connected parks and green spaces in addition to integrated natural areas that prioritize a robust tree canopy and habitat restoration to foster environmental stewardship and social bonds. | Restore and maintain natural habitats. The City should strive to restore and maintain natural habitats in the Hill District through strategic planning, contextual development regulations, and community engagement. | I2.7 | Pollinator conversion program | Project | Implement pollinator gardens where feasible as a short- to mid- range holding strategy for vacant land through the Adopt-a-Lot Program. | X |  |  |  | None needed | Urban Redevelopment Authority, Department of City Planning

## Development Matrix
Goal | Policy | ID | Strategy | PPP | Detail | Timeline |  |  |  | Funding Source | Implementors
[6 empty] | 0-2 | 3-5 | 6-10 | Ongoing
Equitable Economic Development
D1. All developments within the Hill District shall minimize the displacement of residents and businesses. | Limit use of eminent domain. Eminent domain should not be used to acquire occupied property in the Hill District for redevelopment; except in the case of a substantial threat to health or safety. | D1.1 | Alternative methods to eminent domain | Program | Adopt a series of interventions to limit the use of eminent domain including mediation services, community benefits agreements, financial incentives for voluntary sells, land swaps, and community land ownership. |  | X |  |  | None needed | City of Pittsburgh, URA
D1. All developments within the Hill District shall minimize the displacement of residents and businesses. | Provide co-ownership opportunities. All development projects receiving public subsidy from or through the City, County, or URA should provide co- ownership opportunities for Hill District community-based organizations (CBOs) or Hill District faith-based organizations, where possible. | D1.2 | Commercial Community Land Trust | Program | Facilitate the acquisition of land to community land trusts in the Hill District |  |  |  | X | None needed | URA, Pittsburgh Land Bank, The Hill RCOs, Finance Department
D1. All developments within the Hill District shall minimize the displacement of residents and businesses. | Preserve space for Hill District businesses. New development in the Lower Hill must include space for Hill District businesses. | D1.3 | Commercial space renovation | Program | Invest in commercial space renovation and study the feasibility of master leasing commercial spaces on publicly-owned land. |  |  |  | X | Foundations, State and Federal Funding, Land Trusts | URA, The Hill RCOs, Finance Department
D1. All developments within the Hill District shall minimize the displacement of residents and businesses. | Preserve space for Hill District businesses. New development in the Lower Hill must include space for Hill District businesses. | D1.4 | Vacant property matching | Program | Create a program that matches small businesses with property owners of vacant land or commercial buildings. |  | X |  |  | None needed | City of Pittsburgh, URA, Property owners, Small business owners
D1. All developments within the Hill District shall minimize the displacement of residents and businesses. | Commercial set asides for Hill District businesses. All commercial or retail development plans for the Lower Hill District should commit best efforts to achieve a balanced retail mix of local, regional, and national companies. | D1.5 | Financial incentives for commercial set asides | Program | Provide financial incentives such as tax breaks and credits or reduced permit fees to developers that allocate commercial space to local businesses. |  |  |  | X | None needed | DCP, Nonprofit and Private developers, PLI, Finance Department
D2. All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | Prioritize active uses in the Lower Hill. Ground level retail and street activating uses are encouraged as supported by market demand for all new development west of Crawford Street in the Lower Hill. | D2.1 | Development Standards | Project | Establish flexible development standards that promote ground-floor retail in certain areas, including higher ground floor ceiling heights, high transparency, and street facing entryways. |  | X |  |  | None needed | DCP, The Hill RCOs
D2. All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | Implement requirements for minority business participation in new developments. Implement a 30% MBE and 15% WBE requirement for all publicly funded development in the Hill District, all development requiring Site Plan Review or Planning Commission Review, as well as for residential developments in excess of one housing unit. | D2.2 | Formalize a pool of minority businesses | Partnership | Create a bench of minority business organizations that will be eligible to partner in new development opportunities in the Hill District | X |  |  |  | None needed | The Hill RCOs, Local businesses, DCP
D2. All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | Include community input in future development plans. All future redevelopment plans for the Hill District shall incorporate existing community plans. | D2.3 | Update existing neighborhood plans | Program | Establish an inventory of existing neighborhood plans that are regularly updated for future inclusion in redevelopment plans. |  |  |  | X | None needed | The Hill RCOs, DCP
D2. All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | Increase community ownership and participation in development processes. Community residents should be included in all committees relating to the Greater Hill District, inclusive of development and study committees for public and municipal projects in the development stages of any plan or study affecting the neighborhood and community residents. | D2.4 | Connect new development efforts with existing community assets | Program | Utilize the community asset map to easily identify, prioritize, and develop connections with existing assets. A list of active social service businesses, religious organizations, historical places, libraries, schools, education and research centers, public safety providers, and community organizations within the Hill should be provided for partnership consideration when proposing new developments in the neighborhood. |  |  |  | X | None needed | The Hill RCOs, Local businesses, City of Pittsburgh
D3. Land use, public art, and development plans should honor the historical and cultural legacy of the Hill District as a predominately African American neighborhood. Such plans should also abide by any historic preservation standards set by neighborhood preservation entities. | Remove any remnant of Civic Arena/Mellon Arena. Land use and development plans for the Lower Hill shall preserve no physical remnant of Civic Arena/Mellon Arena and the resulting displacement of 8,000+ Hill residents and businesses. | D3.1 | Formalize community engagement | Program | Ensure proactive engagement efforts in new development plans in the Lower Hill that establishes regular updates and clear messaging to communicate goals and benefits of new development without repeating historical mistakes. |  |  |  | X | None needed | DCP, The Hill RCOs
D3. Land use, public art, and development plans should honor the historical and cultural legacy of the Hill District as a predominately African American neighborhood. Such plans should also abide by any historic preservation standards set by neighborhood preservation entities. | Improve access to citywide plans for new development. Community residents should have ready access to all developing and finalized plans, proposals and studies regarding the greater Hill District. input from community residents must be included in the development stages of any plan or study affecting the neighborhood and community residents must have seats on development/study committees whose products will influence the greater Hill District. | D3.2 | Transparent processes | Program | Ensure regular updates to Hill District community-based organizations on related plans and provide easy access to relevant materials and resources. |  |  |  | X | None needed | DCP, The Hill RCOs
D3. Land use, public art, and development plans should honor the historical and cultural legacy of the Hill District as a predominately African American neighborhood. Such plans should also abide by any historic preservation standards set by neighborhood preservation entities. | Incorporate neighborhood characteristics in new development. Development in the Lower Hill District should reflect the social, cultural, and historical characteristics of the Greater Hill District, to the greatest extent possible. | D3.3 | Cultural resource surveys | Project | Conduct and maintain cultural resource surveys to document the historical and social assets of the neighborhood, providing a reference for developers and planners. |  | X |  |  | Foundations, State and Federal Funding, Land Trusts, Grants | Department of City Planning, The Hill Registered Community Organizations
D3. Land use, public art, and development plans should honor the historical and cultural legacy of the Hill District as a predominately African American neighborhood. Such plans should also abide by any historic preservation standards set by neighborhood preservation entities. | Incorporate neighborhood characteristics in new development. Development in the Lower Hill District should reflect the social, cultural, and historical characteristics of the Greater Hill District, to the greatest extent possible. | D3.4 | Permanent art installation | Project | Install a prominent structure, art piece, or gateway signage that honors the history and culture of the Hill District at the intersection of Centre Avenue and Washington Place, the western gateway to the neighborhood. |  |  | X |  | Foundations, Grants | Nonprofit and Private Developers
D4. Hill District residents should have access to secure employment and professional development opportunities resulting from new investments in the neighborhood. | Create new employment opportunities. Local employment opportunities should be expanded through investments and partnerships with community-based organizations. | D4.1 | Community hiring preferences | Partnership | Form a liaison with government, nonprofit, community-based, and private institutions to build a preference program for workers to be placed into new job opportunities within or adjacent to the Hill District in coordination with existing job training programs led by Energy Innovation Center and First Resource Center |  |  |  | X | None needed | Urban Redevelopment Authority, Local Universities, Workforce Development Organizations, The Hill Registered Community Organizations, Housing Authority of The City of Pittsburgh
D4. Hill District residents should have access to secure employment and professional development opportunities resulting from new investments in the neighborhood. | Create new employment opportunities. Local employment opportunities should be expanded through investments and partnerships with community-based organizations. | D4.2 | Job training | Partnership | Build on existing partnerships with universities and local employers to develop catered training and curriculum that meets the needs of Greater Hill residents. |  |  |  | X | None needed | Local universities, Urban Redevelopment Authority, Nonprofit Organizations
D4. Hill District residents should have access to secure employment and professional development opportunities resulting from new investments in the neighborhood. | Introduce “first source” hiring provisions. All development plans shall include "first source" hiring provisions within the project labor agreements for all stages of work at any development site and shall provide hiring priority for Hill District residents and former residents that have been displaced by urban renewal to the greatest extent possible. | D4.3 | Pipeline for "first source" hiring | Partnership | Collaborate with local workforce development organizations to create a pipeline of qualified candidates to fulfill first source hiring provisions. |  | X |  |  | None needed | Urban Redevelopment Authority, Local Universities, Workforce Development Organizations, The Hill Registered Community Organizations
Housing
D5. Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Prioritize building maintenance and rehab in public funding. Funding for building maintenance and rehab should be prioritized in the allocation of funds through the Housing Opportunity Fund managed by the URA. | D5.1 | Maintenance of existing housing stock | Program | Prioritize aging and vacant housing stock for rehab and preservation by conducting and maintaining an inventory of housing stock in need of repair. |  |  |  | X | None needed | Urban Redevelopment Authority, The Hill Registered Community Organizations
D5. Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Mitigate displacement due to new development. All Hill District redevelopments should minimize the involuntary displacement of residents, to the greatest extent feasible, except in the case of a substantial and imminent threat to health or safety. | D5.2 | Anti-displacement program | Program | Adopt an anti-displacement program that prioritizes the needs of residents that are potentially displaced from new development. The program should address topics such as eviction, relocation assistance, and housing preservation |  |  | X |  | State and Federal Funding, Grants | Department of City Planning
D5. Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Mitigate displacement due to new development. All Hill District redevelopments should minimize the involuntary displacement of residents, to the greatest extent feasible, except in the case of a substantial and imminent threat to health or safety. | D5.3 | Right of first offer/first refusal | Program | Community organizations and tenants should have the right of first offer or right of first refusal to purchase affordable housing units. This could mirror Community Opportunity to Purchase Act (COPA) and Tenant Opportunity to Purchase Act (TOPA) initiatives that have been explored in other cities. (HR&A) |  | X |  |  | None needed | Urban Redevelopment Authority, Housing Authority
D5. Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Transition plans for tenants. Publicly subsidized Hill District housing redevelopment plans must include a comprehensive transition plan for existing tenants and a plan preserve existing project based rental subsidy, to the greatest extent possible. | D5.4 | Implement the Bedford Connects Transformation Plan | Program | Public agencies will coordinate with Bedford Dwellings residents on development related to the Bedford Choice Initiative and provide annual updates on the implementation of the Bedford Connects Transformation Plan. |  |  |  | X | None needed | Urban Redevelopment Authority, Housing Authority
D5. Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Prioritize homebuying and homeowner assistance. Public funding in the Hill District should prioritize “equity protection” solutions for homeowners. | D5.5 | Expand Hill District 100 | Program | Work with community organizations to expand the number of properties that are filtered through the Hill District 100 initiative to rehab properties and resale to homeowners. |  |  |  | X | Foundations, Grants | Housing Authority, Permit, Licenses, and Inspections
D5. Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Homeowner rehab assistance. Rehabilitation of owner-occupied homes shall be prioritized in public funding resource allocations for low-income Hill District homeowners. | D5.6 | Define criteria for homeowner rehab assistance | Project | Create clear eligibility criteria for eligible homeowners to ensure assistance is provided to those who need it the most. |  | X |  |  | None needed | Urban Redevelopment Authority, Housing Authority
D5. Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Offer housing options to displaced persons. All housing development plans for the Lower Hill District should provide an admissions preference for displaced persons to the greatest extent possible, including persons who were displaced in the Lower Hill urban renewal effort and their descendants. | D5.7 | Online housing portal | Project | Maintain an online housing portal specifically for displaced persons to facilitate accessible housing opportunities in the Hill District. |  | X |  |  | None needed | Urban Redevelopment Authority, Housing Authority
D6. New development in the Lower Hill must include affordable housing to the greatest extent possible | Promote affordable housing development. New development in the Lower Hill must include affordable housing to the greatest extent possible | D6.1 | Pathways for cooperative housing models | Project | Reduce regulatory barriers to cooperative housing or other innovative community-owned housing models by piloting the design and development of a tenant/ownership structure for cooperative housing in the Lower Hill. |  |  | X |  | None needed | Department of City Planning
D6. New development in the Lower Hill must include affordable housing to the greatest extent possible | Housing databases. Actively maintain a comprehensive housing database for the Hill District that tracks new affordable housing units created through development plans. | D6.2 | Housing databases | Program | Actively maintain a comprehensive housing database for the Hill District that tracks new affordable housing units created through development plans. |  |  | X |  | None needed | Urban Redevelopment Authority, Housing Authority
Land Use and Zoning
D7. A comprehensive land use management strategy should be developed for the Hill District, prioritizing community-driven zoning recommendations and the identified use of vacant land and buildings, with a focus on the stewardship of community stakeholders. | Engage community members in citywide zoning efforts. Establish community participation in the future rezoning of the Hill District. | D7.1 | Draft zoning recommendations | Program | In coordination with community organizations, draft priority zoning recommendations to be included in the future citywide update of the comprehensive plan. | X |  |  |  | None needed | Hill District RCOs, Department of City Planning
D7. A comprehensive land use management strategy should be developed for the Hill District, prioritizing community-driven zoning recommendations and the identified use of vacant land and buildings, with a focus on the stewardship of community stakeholders. | Prioritize community organizations and priorities in the disposition of vacant land. Community service organizations and groups based in the Hill District should be given priority to acquire vacant land and buildings as needed for educational, social service, and recreational opportunities to improve quality of life for Hill District residents. | D7.2 | Technical assistance to community organizations | Partnership | Expand technical assistance to community organizations in partnership with existing real estate assistance providers such as Neighborhood Allies, Riverside Center for Innovation, and local universities to identify potential vacant properties for acquisition and creating proposals for redevelopment. Technical assistance should also include guidance on addressing pre-development expenses and funding sources related to remediation of brownfield and undermine sites. |  | X |  |  | Foundations, Grants | Urban Redevelopment Authority, Real Estate Assistance Providers
D7. A comprehensive land use management strategy should be developed for the Hill District, prioritizing community-driven zoning recommendations and the identified use of vacant land and buildings, with a focus on the stewardship of community stakeholders. | Prioritize community organizations and priorities in the disposition of vacant land. Community service organizations and groups based in the Hill District should be given priority to acquire vacant land and buildings as needed for educational, social service, and recreational opportunities to improve quality of life for Hill District residents. | D7.3 | Vacant property stabilization | Program | Prioritize the stabilization of vacant properties before demolition. Stabilization should include securing the property, maintenance and clean-up, structural assessments, and planning for future use. |  |  |  | X | Foundations, Grants, State and Federal Funding, City Capital Budget | Urban Redevelopment Authority, Housing Authority, Department of City Planning, Permits, Licensing, and Inspections, Pittsburgh Land Bank
D7. A comprehensive land use management strategy should be developed for the Hill District, prioritizing community-driven zoning recommendations and the identified use of vacant land and buildings, with a focus on the stewardship of community stakeholders. | Prioritize community organizations and priorities in the disposition of vacant land. Community service organizations and groups based in the Hill District should be given priority to acquire vacant land and buildings as needed for educational, social service, and recreational opportunities to improve quality of life for Hill District residents. | D7.4 | Community identified uses for vacant land | Program | Evaluate appropriate parcels that would not be suitable for commercial or residential uses and dedicate these lots toward priorities that have been identified by community organizations. This could include green infrastructure, open space, renewable energy, or other uses. This strategy should be conducted in coordination with ongoing city-led and city-wide efforts related to vacant land. |  | X |  |  | None needed | DCP, The Hill RCOs
D7. A comprehensive land use management strategy should be developed for the Hill District, prioritizing community-driven zoning recommendations and the identified use of vacant land and buildings, with a focus on the stewardship of community stakeholders. | Prioritize community organizations and priorities in the disposition of vacant land. Community service organizations and groups based in the Hill District should be given priority to acquire vacant land and buildings as needed for educational, social service, and recreational opportunities to improve quality of life for Hill District residents. | D7.5 | Comprehensive plan for vacant land | Project | Work with the Pittsburgh Land Bank and the URA to create a vacant land strategy for all vacant land in the Hill District. This should build on existing plans while outline. |  | X |  |  | None needed | Urban Redevelopment Authority, Housing Authority, Department of City Planning, Pittsburgh Land Bank
Urban Sustainable Design
D8. All plans for the Hill District should include provisions for green and sustainable development. | Implement standards for sustainable design. Hill District redevelopments should include ample green space, trees, parks and playgrounds, and LEED certified building standards, as outlined in the Hill District Green Print and other plans. | D8.1 | Expand open space | Project | Create a series of pocket parks with playgrounds, benches, tables, and basketball courts on vacant lots in the Hill District where there are few nearby opportunities to access maintained green space |  |  |  | X | City Capital Budget, State and Federal Funding | Department of Parks and Recreation, Urban Redevelopment Authority
D8. All plans for the Hill District should include provisions for green and sustainable development. | Implement standards for sustainable design. Hill District redevelopments should include ample green space, trees, parks and playgrounds, and LEED certified building standards, as outlined in the Hill District Green Print and other plans. | D8.2 | Green development | Program | Adopt green building techniques in all new development such as the use of high-quality insulation materials, rainwater harvesting infrastructure, renewable materials, and native plants and trees for landscaping. |  |  |  | X | None needed | Department of City Planning, Permits, Licensing, and Inspections
D9. The design of redevelopment projects enhance the social, cultural, and historic characteristics of the greater Hill District’s built and natural environment. | Contextual development plans. All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | D9.1 | Views in the Hill District | Program | The design review process for all new proposed projects should seek to preserve the views from the Hill District in all directions. |  |  |  | X | None needed | Department of City Planning, Permits, Licensing, and Inspections
D9. The design of redevelopment projects enhance the social, cultural, and historic characteristics of the greater Hill District’s built and natural environment. | Contextual development plans. All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | D9.2 | Renewable Energy | Program | Develop a neighborhood-level solar or other alternative energy program to provide clean, cheap energy to Hill District residents and businesses. |  |  |  | X | Foundations, Grants, State and Federal Funding | Department of Public Works
D9. The design of redevelopment projects enhance the social, cultural, and historic characteristics of the greater Hill District’s built and natural environment. | Acknowledge existing development patterns in the Hill District. Recognizing the major arterials for the Hill District as identified through the corridor analyses (Webster Ave, Herron Ave, Centre Ave), the design of all new development should acknowledge that the Hill District is primarily a residential neighborhood with neighborhood business districts that are at the edge of the Pittsburgh Central Business District. | D9.3 | Context-sensitive design standards | Project | Identify neighborhood characteristics that preserve and enhance the existing built environment and apply appropriate design standards that reflect and reinforce that character. |  |  | X |  | None needed | Department of City Planning
Commercial Corridors
D10. A commercially viable and attractive experience should be created along Herron and the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Facilitate the streamlining of city funds and resources to reduce predevelopment cost burdens. Since Herron Avenue has a large undermining overlay, environmental remediation costs can be very high. The City should facilitate funds that support predevelopment costs. | D10.1 | Targeted grant opportunities | Program | Utilize federal and local funding to support developers with predevelopment costs for potential development along Herron Avenue, similar to previous efforts along Center Avenue. |  |  |  | X | State and Federal Funding | Urban Redevelopment Authority, Real Estate Assistance Providers
D10. A commercially viable and attractive experience should be created along Herron and the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Facilitate the streamlining of city funds and resources to reduce predevelopment cost burdens. Since Herron Avenue has a large undermining overlay, environmental remediation costs can be very high. The City should facilitate funds that support predevelopment costs. | D10.2 | Technical support for local developers | Program | Provide adequate staff time and other city resources to streamline permitting and other regulatory processes on Herron Avenue. Formalize connections between local partners and developers for navigating the development process |  |  |  | X | None needed | Urban Redevelopment Authority, Department of City Planning, Permits, Licensing, and Inspections
D10. A commercially viable and attractive experience should be created along Herron and the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Facilitate the streamlining of city funds and resources to reduce predevelopment cost burdens. Since Herron Avenue has a large undermining overlay, environmental remediation costs can be very high. The City should facilitate funds that support predevelopment costs. | D10.3 | Tailored community training for grant applications | Program | Promote training opportunities for applying for all federal, state, regional and local grants that are relevant to environmental mitigation costs of sites. A grant application that presents the overall strategy for all land parcels will have a greater potential of winning competitive non-local grants. This would require a massing plus costs study of all projects proposed on Herron Avenue and the anticipated remediation costs for those sites. |  |  |  | X | None needed | Urban Redevelopment Authority, Real Estate Assistance Providers
D10. A commercially viable and attractive experience should be created along Herron and the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Tailored disposition process for vacant land. Prioritize revitalization of vacant land along Herron Avenue using a strategic and organized disposition process. | D10.4 | Embedded community goals in land disposition RFQs | Program | If the URA solicits developers for land disposition on Herron Avenue, those developers must be provided with details on available partnerships with community groups or methods to utilize existing community assets to strengthen the community ties of proposed projects to the existing community. |  |  |  | X | None needed | Urban Redevelopment Authority, Nonprofit and Private Developers
D10. A commercially viable and attractive experience should be created along Herron and the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Tailored disposition process for vacant land. Prioritize revitalization of vacant land along Herron Avenue using a strategic and organized disposition process. | D10.5 | Vacant land prioritziation | Program | In partnership with the Hill CDC and community groups, a development prioritization plan should be created for parcels on Herron Avenue. |  |  |  | X | Foundations, Grants | Urban Redevelopment Authority, Housing Authority, Department of City Planning, Hill CDC