## Implementation Matrix
Goal | Policy | ID | Strategy | PPP | Detail | Timeline |  |  |  | Funding Source | Implementors
[6 empty] | 0-2 | 3-5 | 6-10 | Ongoing
All developments within the Hill District shall minimize the displacement of residents and businesses. | Policy: Limit use of eminent domain. Eminent domain should not be used to acquire occupied property in the Hill District for redevelopment; except in the case of a substantial threat to health or safety. | D1 | Alternative methods to eminent domain | Program | Adopt a series of interventions to limit the use of eminent domain including mediation services, community benefits agreements, financial incentives for voluntary sells, land swaps, and community land ownership. |  | X |  |  | None needed | City of Pittsburgh, URA
All developments within the Hill District shall minimize the displacement of residents and businesses. | Policy: Provide co-ownership opportunities. All development projects receiving public subsidy from or through the City, County, or URA should provide co- ownership opportunities for Hill District community-based organizations (CBOs) or Hill District faith-based organizations, where possible. | D2 | Commercial Community Land Trust | Program | Facilitate the acquisition of land to community land trusts in the Hill District |  |  |  | X | None needed | URA, Pittsburgh Land Bank, The Hill RCOs, Finance Department
All developments within the Hill District shall minimize the displacement of residents and businesses. | Policy: Preserve space for Hill District businesses. New development in the Lower Hill must include space for Hill District businesses. (GHDMP Appendix) | D3 | Commercial space renovation | Program | Invest in commercial space renovation and study the feasibility of master leasing commercial spaces on publicly-owned land. |  |  |  | X | Foundations, State and Federal Funding, Land Trusts | URA, The Hill RCOs, Finance Department
All developments within the Hill District shall minimize the displacement of residents and businesses. | Policy: Preserve space for Hill District businesses. New development in the Lower Hill must include space for Hill District businesses. (GHDMP Appendix) | D4 | Vacant property matching | Program | Create a program that matches small businesses with property owners of vacant land or commercial buildings. |  | X |  |  | None needed | City of Pittsburgh, Property owners, Small business owners
All developments within the Hill District shall minimize the displacement of residents and businesses. | Policy - Commercial Set Asides for Hill District Businesses. All commercial or retail development plans for the Lower Hill District should commit best efforts to achieve a balanced retail mix of local, regional, and national companies. | D5 | Financial incentives for commercial set asides | Program | Provide financial incentives such as tax breaks and credits or reduced permit fees to developers that allocate commercial space to local businesses. |  |  |  | X | None needed | DCP, Nonprofit and Private developers, PLI, Finance Department
All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | Prioritize active uses in the Lower Hill. Ground level retail and street activating uses are encouraged as supported by market demand for all new development west of Crawford Street in the Lower Hill. | D6 | Development Standards | Project | Establish flexible development standards that promote ground-floor retail in certain areas, including higher ground floor ceiling heights, high transparency, and street facing entryways. |  | X |  |  | None needed | DCP, The Hill RCOs
All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | Implement requirements for minority business participation in new developments. Implement a 30% MBE and 15% WBE requirement for all publicly funded development in the Hill District, all development requiring Site Plan Review or Planning Commission Review, as well as for residential developments in excess of one housing unit. | D7 | Formalize a pool of minority businesses | Partnership | Create a bench of minority business organizations that will be eligible to partner in new development opportunities in the Hill District | X |  |  |  | None needed | The Hill RCOs, Local businesses, DCP
All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | Include community input in future development plans. All future redevelopment plans for the Hill District shall incorporate existing community plans. | D8 | Update existing neighborhood plans | Program | Establish an inventory of existing neighborhood plans that are regularly updated for future inclusion in redevelopment plans. |  |  |  | X | None needed | The Hill RCOs, DCP
All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | Increase community ownership and participation in development processes. Community residents should be included in all committees relating to the Greater Hill District, inclusive of development and study committees for public and municipal projects in the development stages of any plan or study affecting the neighborhood and community residents. | D9 | Connect new development efforts with existing community assets | Program | Utilize the community asset map to easily identify, prioritize, and develop connections with existing assets. A list of active social service businesses, religious organizations, historical places, libraries, schools, education and research centers, public safety providers, and community organizations within the Hill should be provided for partnership consideration when proposing new developments in the neighborhood. |  |  |  | X | None needed | The Hill RCOs, Local businesses, City of Pittsburgh
Land use, public art, and development plans should honor the historical and cultural legacy of the Hill District as a predominately African American neighborhood. Such plans should also abide by any historic preservation standards set by neighborhood preservation entities. | Remove any remnant of Civic Arena/Mellon Arena. Land use and development plans for the Lower Hill shall preserve no physical remnant of Civic Arena/Mellon Arena and the resulting displacement of 8,000+ Hill residents and businesses. | D10 | Formalize community engagement | Program | Ensure proactive engagement efforts in new development plans in the Lower Hill that establishes regular updates and clear messaging to communicate goals and benefits of new development without repeating historical mistakes. |  |  |  | X | None needed | DCP, The Hill RCOs
Land use, public art, and development plans should honor the historical and cultural legacy of the Hill District as a predominately African American neighborhood. Such plans should also abide by any historic preservation standards set by neighborhood preservation entities. | Improve access to citywide plans for new development. Community residents should have ready access to all developing and finalized plans, proposals and studies regarding the greater Hill District. input from community residents must be included in the development stages of any plan or study affecting the neighborhood and community residents must have seats on development/study committees whose products will influence the greater Hill District. | D11 | Transparent processes | Program | Ensure regular updates to Hill District community-based organizations on related plans and provide easy access to relevant materials and resources. |  |  |  | X | None needed | DCP, The Hill RCOs
Land use, public art, and development plans should honor the historical and cultural legacy of the Hill District as a predominately African American neighborhood. Such plans should also abide by any historic preservation standards set by neighborhood preservation entities. | Incorporate neighborhood characteristics in new development. Development in the Lower Hill District should reflect the social, cultural, and historical characteristics of the Greater Hill District, to the greatest extent possible. | D12 | Cultural resource surveys | Project | Conduct and maintain cultural resource surveys to document the historical and social assets of the neighborhood, providing a reference for developers and planners. |  | X |  |  | Foundations, State and Federal Funding, Land Trusts, Grants | DCP, The Hill RCOs
Land use, public art, and development plans should honor the historical and cultural legacy of the Hill District as a predominately African American neighborhood. Such plans should also abide by any historic preservation standards set by neighborhood preservation entities. | Incorporate neighborhood characteristics in new development. Development in the Lower Hill District should reflect the social, cultural, and historical characteristics of the Greater Hill District, to the greatest extent possible. | D13 | Permanent art installation | Project | Install a prominent structure, art piece, or gateway signage that honors the history and culture of the Hill District at the intersection of Centre Avenue and Washington Place, the western gateway to the neighborhood. |  |  | X |  | Foundations, Grants | Nonprofit and Private Developers
Hill District residents should have access to secure employment and professional development opportunities resulting from new investments in the neighborhood. | Create new employment opportunities. Local employment opportunities should be expanded through investments and partnerships with community-based organizations. | D14 | Community hiring preferences | Partnership | Form a liaison with government, nonprofit, community-based, and private institutions to build a preference program for workers to be placed into new job opportunities within or adjacent to the Hill District in coordination with existing job training programs led by Energy Innovation Center and First Resource Center |  |  |  | X | None needed | URA, Local Universities, Workforce Development Organizations, The Hill RCOs
Hill District residents should have access to secure employment and professional development opportunities resulting from new investments in the neighborhood. | Create new employment opportunities. Local employment opportunities should be expanded through investments and partnerships with community-based organizations. | D15 | Job training | Partnership | Build on existing partnerships with universities and local employers to develop catered training and curriculum that meets the needs of Greater Hill residents. |  |  |  | X | None needed | Local universities, URA, Nonprofit Organizations
Hill District residents should have access to secure employment and professional development opportunities resulting from new investments in the neighborhood. | Introduce “first source” hiring provisions. All development plans shall include "first source" hiring provisions within the project labor agreements for all stages of work at any development site and shall provide hiring priority for Hill District residents and former residents that have been displaced by urban renewal to the greatest extent possible. | D16 | Pipeline for first source hiring | Partnership | Collaborate with local workforce development organizations to create a pipeline of qualified candidates to fulfill first source hiring provisions. |  | X |  |  | None needed | URA, Local Universities, Workforce Development Organizations, The Hill RCOs
Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Prioritize building maintenance and rehab in public funding. Funding for building maintenance and rehab should be prioritized in the allocation of funds through the Housing Opportunity Fund managed by the URA. | D17 | Maintenance of existing housing stock | Program | Prioritize aging and vacant housing stock for rehab and preservation by conducting and maintaining an inventory of housing stock in need of repair. |  |  |  | X | None needed | URA, The Hill RCOs
Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Prioritize building maintenance and rehab in public funding. Funding for building maintenance and rehab should be prioritized in the allocation of funds through the Housing Opportunity Fund managed by the URA. | D18 | Anti-displacement program | Program | Adopt an anti-displacement program that prioritizes the needs of residents that are potentially displaced from new development. The program should address topics such as eviction, relocation assistance, and housing preservation |  |  | X |  | State and Federal Funding, Grants | DCP
Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Prioritize building maintenance and rehab in public funding. Funding for building maintenance and rehab should be prioritized in the allocation of funds through the Housing Opportunity Fund managed by the URA. | D19 | Right of first offer/first refusal | Program | Community organizations and tenants should have the right of first offer or right of first refusal to purchase affordable housing units. This could mirror Community Opportunity to Purchase Act (COPA) and Tenant Opportunity to Purchase Act (TOPA) initiatives that have been explored in other cities. (HR&A) |  | X |  |  | None needed | URA, Housing Authority
Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Transition plans for tenants. Publicly subsidized Hill District housing redevelopment plans must include a comprehensive transition plan for existing tenants and a plan preserve existing project based rental subsidy, to the greatest extent possible | D20 | Implement the Bedford Connects Transformation Plan | Program | Public agencies will coordinate with Bedford Dwellings residents on development related to the Bedford Choice Initiative and provide annual updates on the implementation of the Bedford Connects Transformation Plan. |  |  |  | X | None needed | URA, Housing Authority
Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Prioritize homebuying and homeowner assistance. Public funding in the Hill District should prioritize “equity protection” solutions for homeowners | D21 | Expand Hill District 100 | Program | Work with community organizations to expand the number of properties that are filtered through the Hill District 100 initiative to rehab properties and resale to homeowners. |  |  |  | X | Foundations, Grants | Housing Authority, Permit, Licenses, and Inspections
Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Homeowner rehab assistance. Rehabilitation of owner-occupied homes shall be prioritized in public funding resource allocations for low-income Hill District homeowners. | D22 | Define criteria for homeowner rehab assistance | Project | Create clear eligibility criteria for eligible homeowners to ensure assistance is provided to those who need it the most. |  | X |  |  | None needed | URA, Housing Authority
Displacement risks for existing residents should be mitigated and the return of formerly displaced Hill District residents should be facilitated. | Offer housing options to displaced persons. All housing development plans for the Lower Hill District should provide an admissions preference for displaced persons to the greatest extent possible, including persons who were displaced in the Lower Hill urban renewal effort and their descendants. | D23 | Online housing portal | Project | Maintain an online housing portal specifically for displaced persons to facilitate accessible housing opportunities in the Hill District. |  | X |  |  | None needed | URA, Housing Authority
New development in the Lower Hill must include affordable housing to the greatest extent possible | Promote affordable housing development. New development in the Lower Hill must include affordable housing to the greatest extent possible. | D24 | Pathways for cooperative housing models | Project | Reduce regulatory barriers to cooperative housing or other innovative community-owned housing models by piloting the design and development of a tenant/ownership structure for cooperative housing in the Lower Hill. |  |  | X |  | None needed | Department of City Planning
New development in the Lower Hill must include affordable housing to the greatest extent possible | Create more opportunities for housing at different income levels. At least 30% of housing units in all housing development plans in the Lower Hill shall, to the greatest extent feasible and subject to the regulations associated with any housing assistance resources utilized, be affordable to very-low income households (at for below 50% AMI). If public funding is used or if a project-based subsidy is available, at least 50% of the affordable units must, to the greatest extent feasible and subject to the regulations of any housing assistance resources utilized, be affordable to extremely-low income households (at or below 30% AMI). In allocating housing and community development resources, the City and URA should encourage a higher percentage of affordability and/or the use of deep subsidies to achieve deeper income targeting. | D25 | Housing databases | Program | Actively maintain a comprehensive housing database for the Hill District that tracks new affordable housing units created through development plans. |  |  | X |  | None needed | URA, Housing Authority
A comprehensive management strategy for vacant land and buildings in the Hill District should prioritize the stewardship of community stakeholders | Prioritize community organizations and priorities in the disposition of vacant land. Community service organizations and groups based in the Hill District should be given a priority to acquire vacant land and buildings as needed for educational, social service, and recreational opportunities to improve quality of life for Hill District residents. | D26 | Technical assistance to community organizations | Partnership | Expand technical assistance to community organizations in partnership with existing real estate assistance providers such as Neighborhood Allies, Riverside Center for Innovation, and local universities to identify potential vacant properties for acquisition and creating proposals for redevelopment. Technical assistance should also include guidance on addressing pre-development expenses and funding sources related to remediation of brownfield and undermine sites. |  | X |  |  | Foundations, Grants | URA, Real Estate Assistance Providers
A comprehensive management strategy for vacant land and buildings in the Hill District should prioritize the stewardship of community stakeholders | Prioritize community organizations and priorities in the disposition of vacant land. Community service organizations and groups based in the Hill District should be given a priority to acquire vacant land and buildings as needed for educational, social service, and recreational opportunities to improve quality of life for Hill District residents. | D27 | Vacant property stabilization | Program | Prioritize the stabilization of vacant properties before demolition. Stabilization should include securing the property, maintenance and clean-up, structural assessments, and planning for future use. |  |  |  | X | Foundations, Grants, State and Federal Funding, City Capital Budget | URA, Housing Authority, DCP, PLI
A comprehensive management strategy for vacant land and buildings in the Hill District should prioritize the stewardship of community stakeholders | Prioritize community organizations and priorities in the disposition of vacant land. Community service organizations and groups based in the Hill District should be given a priority to acquire vacant land and buildings as needed for educational, social service, and recreational opportunities to improve quality of life for Hill District residents. | D28 | Community identified uses for vacant land | Program | Evaluate appropriate parcels that would not be suitable for commercial or residential uses and dedicate these lots toward priorities that have been identified by community organizations. This could include green infrastructure, open space, renewable energy, or other uses. This strategy should be conducted in coordination with ongoing city-led and city-wide efforts related to vacant land. |  | X |  |  | None needed | DCP, The Hill RCOs
A comprehensive management strategy for vacant land and buildings in the Hill District should prioritize the stewardship of community stakeholders | Prioritize community organizations and priorities in the disposition of vacant land. Community service organizations and groups based in the Hill District should be given a priority to acquire vacant land and buildings as needed for educational, social service, and recreational opportunities to improve quality of life for Hill District residents. | D29 | Comprehensive plan for vacant land | Project | Work with the Pittsburgh Land Bank and the URA to create a vacant land strategy for all vacant land in the Hill District. This should build on existing plans while outline. |  | X |  |  | None needed | URA, Housing Authority, DCP, Pittsburgh Land Bank
All plans for the Hill District should include provisions for green and sustainable development. | Implement standards for sustainable design. Hill District redevelopments should include ample green space, trees, parks and playgrounds, and LEED certified building standards, as outlined in the Hill District Green Print and other plans. | D30 | Expand open space | Project | Create a series of pocket parks with playgrounds, benches, tables, and basketball courts on vacant lots in the Hill District where there are few nearby opportunities to access maintained green space |  |  |  | X | City Capital Budget, State and Federal Funding | Parks and Recreation, URA
All plans for the Hill District should include provisions for green and sustainable development. | Implement standards for sustainable design. Hill District redevelopments should include ample green space, trees, parks and playgrounds, and LEED certified building standards, as outlined in the Hill District Green Print and other plans. | D31 | Green development | Program | Adopt green building techniques in all new development such as the use of high-quality insulation materials, rainwater harvesting infrastructure, renewable materials, and native plants and trees for landscaping. |  |  |  | X | None needed | DCP, PLI
The design of redevelopment projects enhance the social, cultural, and historic characteristics of the greater Hill District’s built and natural environment. | Contextual development plans. All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | D32 | Views in the Hill District | Program | The design review process for all new proposed projects should seek to preserve the views from the Hill District in all directions. |  |  |  | X | None needed | DCP, PLI
The design of redevelopment projects enhance the social, cultural, and historic characteristics of the greater Hill District’s built and natural environment. | Contextual development plans. All development plans should be designed to benefit existing and future community residents and businesses, while allowing for future growth of retail, residential, and commercial spaces. | D33 | Renewable Energy | Program | Develop a neighborhood-level solar or other alternative energy program to provide clean, cheap energy to Hill District residents and businesses. |  |  |  | X | Foundations, Grants, State and Federal Funding | DPW
The design of redevelopment projects enhance the social, cultural, and historic characteristics of the greater Hill District’s built and natural environment. | Acknowledge existing development patterns in the Hill District. Recognizing the major arterials for the Hill District as identified through the corridor analyses (Webster Ave, Herron Ave, Centre Ave), the design of all new development should acknowledge that the Hill District is primarily a residential neighborhood with neighborhood business districts that are at the edge of the Pittsburgh Central Business District. | D34 | Context-sensitive design standards | Project | Identify neighborhood characteristics that preserve and enhance the existing built environment and apply appropriate design standards that reflect and reinforce that character. |  |  | X |  | None needed | DCP
A commercially viable and attractive experience should be created along Herron the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Facilitate the streamlining of city funds and resources to reduce predevelopment cost burdens. Since Herron Avenue has a large undermining overlay, environmental remediation costs can be very high. The City should facilitate funds that support predevelopment costs. | D35 | Targeted grant opportunities | Program | Utilize federal and local funding to support developers with predevelopment costs for potential development along Herron Avenue, similar to previous efforts along Center Avenue. |  |  |  | X | State and Federal Funding | URA, Real Estate Assistance Providers
A commercially viable and attractive experience should be created along Herron the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Facilitate the streamlining of city funds and resources to reduce predevelopment cost burdens. Since Herron Avenue has a large undermining overlay, environmental remediation costs can be very high. The City should facilitate funds that support predevelopment costs. | D36 | Technical support for local developers | Program | Provide adequate staff time and other city resources to streamline permitting and other regulatory processes on Herron Avenue. Formalize connections between local partners and developers for navigating the development process |  |  |  | X | None needed | URA, DCP, PLI
A commercially viable and attractive experience should be created along Herron the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Facilitate the streamlining of city funds and resources to reduce predevelopment cost burdens. Since Herron Avenue has a large undermining overlay, environmental remediation costs can be very high. The City should facilitate funds that support predevelopment costs. | D37 | Tailored community training for grant applications | Program | Promote training opportunities for applying for all federal, state, regional and local grants that are relevant to environmental mitigation costs of sites. A grant application that presents the overall strategy for all land parcels will have a greater potential of winning competitive non-local grants. This would require a massing plus costs study of all projects proposed on Herron Avenue and the anticipated remediation costs for those sites. |  |  |  | X | None needed | URA, Real Estate Assistance Providers
A commercially viable and attractive experience should be created along Herron the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Tailored disposition process for vacant land. Prioritize revitalization of vacant land along Herron Avenue using a strategic and organized disposition process. | D38 | Embedded community goals in land disposition RFQs | Program | If the URA solicits developers for land disposition on Herron Avenue, those developers must be provided with details on available partnerships with community groups or methods to utilize existing community assets to strengthen the community ties of proposed projects to the existing community. |  |  |  | X | None needed | URA, Nonprofit and Private Developers
A commercially viable and attractive experience should be created along Herron the community’s commercial corridors to benefit the Hill District and serve as connectors to neighboring communities. | Vacant land prioritization. In partnership with the Hill District land bank and community groups, a development prioritization plan should be created for parcels on Herron Avenue. | D39 | Vacant land prioritziation | Program | In partnership with the Hill CDC and community groups, a development prioritization plan should be created for parcels on Herron Avenue. |  |  |  | X | Foundations, Grants | URA, Housing Authority, DCP, Hill CDC